## Sheet1
State of Readiness Resource Planning
|  |  | Est. Low (Hours) | Est. High (Hours)
|  |  | Assumes team of 1, basic site, 60 pages | Assumes team of 5, complex site 250 pages
Total Hours |  |  | 151.5 | 423.25
| Hours per resource |  | 151.5 | 84.65
| Estimated number of weeks assuming 20 hrs/week |  | 7.575 | 4.2325
Breakdown
Plan Your Site
| Take the Training |  | 1 | 5
| Resource your team |  | 1 | 2
| Develop your business strategy |  | 15 | 37.5
Set your objectives
Clarify your audiences
Identify key messages
Define success measurements
Prepare Your Content
| Take the Training |  | 0.5 | 2.5
| Conduct Inventory and Assess Quality |  | 15 | 90
Create an inventory
Assess quality
| Take the Training |  | 1 | 5
| Revising and Preparing Content |  | 67.5 | 281.25
Identify what needs to be created
Write to support key messages
Edit for tone and style
Select and prepare images
DRAFT v2 5/19/11